## Sheet1
complete
taken
blocked
Item | Person | estimate | comments
Music triggers for BGM |  | 1h max | ring around fire for main bgm, line contoured to land edge for stars, noise in the middle
bugs running for fire set direction to face fire when stop moving |  | trivial
define enclaves | Lex | 3h | set dev names for each gathering/village
define characters in enclaves |  | 3h | determine list of people and roles in each enclave
more dialogue |  | idk 30h | dialogue for everyone (will split out into separate tasks once above is complete)
fine tweaking of bug positions at end |  | 3-4h
dialogue handler next text button |  |  | e.g. Space to immediately display next text or next option
dialogue handler summary text button |  |  | e.g. q to skip all dialogue until your next turn and display summary text
pause screen text | Lex | 1h
options page | Lex |  | accessible via keypress from pause screen
dialogue options
music volume
intro screen
outro fade to black
outro image
define cricket character type
define rhino beetle character type
sfx for chat self | Lex
sfx for chat other - firefly | Lex
sfx for chat other - cricket | Lex
sfx for chat other - beetle | Lex
sfx for mining
rewire chat sfx to set in character
alter dialoguehandler to read true or false for sfx
wire in separate flag for sound type
set sound type definitions in character def
sfx attenuate re. player position
sfx only trigger within certain proximity of player
alter ground def to set 3x3 tiles in center as invulnerable
character interaction triggered by picking up item |  |  | to use for beetles, who have placed emeralds at edge of map to stop it crumbling further
replace excavactor with non-functional excavator ruin |  |  | the beetles plundered this; build your own elsewhere; may have to adjust balance as a result of this change
sprite sheet for cricket
sprite sheet for beetle
multiple sets of dialogue for workers, depending on character category flag |  |  | then subsets of people can have different dialogue and the old dude can e.g. refuse to do shit which can then be excluded from options, or have further dialogue
level out fire decay at end
endgame music
endgame dialogue options
end screen music
separate ambience track for intro screen | Lex | 1-2h
intro screen
clean up firefly_fueler_makeaxe dialogue patch | Lex | 1h
relabel fireflies + firefly name refs to make more sense | Lex | 1h